## _Config
Field | Value | Description
String | ObjectId | String
CalendarObjectId | 939 | Global Calendar ObjectId (939 = Corporate Full Time)
OBSObjectId | 745 | OBS ObjectId (745 = E&C)
CurrencyObjectId | 1 | Currency ObjectId (1 = USD)

## Project
ObjectId | Id | Name | Status | OBSObjectId | ParentEPSObjectId | WBSObjectId | PlannedStartDate | ScheduledFinishDate | DataDate | ActivityIdPrefix | ActivityIdSuffix | ActivityIdIncrement | ActivityDefaultCalendarObjectId | ActivityDefaultDurationType | ActivityDefaultActivityType | ActivityDefaultPercentCompleteType | OriginalBudget | LevelingPriority | GUID | AddedBy | CriticalActivityPathType | CriticalActivityFloatLimit | EarnedValueComputeType | EarnedValueETCComputeType | WBSCodeSeparator | SummarizeToWBSLevel | SummaryLevel
ObjectId | String | String | Enum | ObjectId | ObjectId | ObjectId | Date | Date | Date | String | String | Integer | ObjectId | Enum | Enum | Enum | Cost | Integer | String | String | Enum | Duration | Enum | Enum | String | Boolean | Enum
1018 | DE1000 | DE1000 Project | Active | 745 | 3667 | 1019 | 2014-02-03T00:00:00 | 2014-10-17T00:00:00 | 2014-01-01T00:00:00 | CE | 1000 | 10 | 939 | Fixed Duration and Units/Time | Task Dependent | Duration | 0.000000 | 10 | {8AA09FB4-6CC6-4C4D-85CF-178AFAEFBB41} | admin | Critical Float | 0.00 | Activity Percent Complete | PF = 1 / CPI | . | 0 | Assignment Level

## WBS
ObjectId | Code | Name | ProjectObjectId | ParentObjectId | OBSObjectId | Status | SequenceNumber | OriginalBudget | EarnedValueComputeType | EarnedValueETCComputeType | EarnedValueETCUserValue | EarnedValueUserPercent | IndependentETCLaborUnits | IndependentETCTotalCost | GUID | UDF_TypeObjectId | UDF_IndicatorValue
ObjectId | String | String | ObjectId | ObjectId | ObjectId | Enum | Integer | Cost | Enum | Enum | Float | Float | Unit | Cost | String | ObjectId | Enum
1015 | 1 | a | 1018 |  | 745 | Active | 0 | 0.000000 | Activity Percent Complete | PF = 1 / CPI | 0 | 0.0 | 0.000000 | 0.000000 | {9A176C14-C522-445A-B583-27D67E498A85} | 1070 | Green
1016 | 2 | b | 1018 |  | 745 | Active | 1 | 0.000000 | Activity Percent Complete | PF = 1 / CPI | 0 | 0.0 | 0.000000 | 0.000000 | {B3EE5FEA-6B42-4F3C-8B18-17ACF4D449A1} | 1070 | Green
1017 | 3 | c | 1018 |  | 745 | Active | 2 | 0.000000 | Activity Percent Complete | PF = 1 / CPI | 0 | 0.0 | 0.000000 | 0.000000 | {72388AB4-B764-4F4E-8AED-53A9C66939CA} | 1070 | Green

## Activity
ObjectId | Id | Name | ProjectObjectId | WBSObjectId | Type | Status | CalendarObjectId | PlannedStartDate | PlannedFinishDate | PlannedDuration | ActualStartDate | ActualFinishDate | ActualDuration | RemainingDuration | RemainingEarlyStartDate | RemainingEarlyFinishDate | RemainingLateStartDate | RemainingLateFinishDate | StartDate | FinishDate | PercentComplete | PercentCompleteType | PhysicalPercentComplete | DurationPercentComplete | UnitsPercentComplete | PlannedLaborCost | PlannedLaborUnits | PlannedNonLaborCost | PlannedNonLaborUnits | ActualLaborCost | ActualLaborUnits | ActualNonLaborCost | ActualNonLaborUnits | RemainingLaborCost | RemainingLaborUnits | RemainingNonLaborCost | RemainingNonLaborUnits | AtCompletionDuration | AtCompletionLaborCost | AtCompletionLaborUnits | AtCompletionNonLaborCost | AtCompletionNonLaborUnits | AtCompletionExpenseCost | DurationType | LevelingPriority | AutoComputeActuals | PrimaryResourceObjectId | EstimatedWeight | PrimaryConstraintType | PrimaryConstraintDate | GUID | Code1_TypeObjectId | Code1_ValueObjectId | Code2_TypeObjectId | Code2_ValueObjectId | Code3_TypeObjectId | Code3_ValueObjectId | Code4_TypeObjectId | Code4_ValueObjectId
ObjectId | String | String | ObjectId | ObjectId | Enum | Enum | ObjectId | Date | Date | Duration | Date | Date | Duration | Duration | Date | Date | Date | Date | Date | Date | Float | Enum | Float | Float | Float | Cost | Unit | Cost | Unit | Cost | Unit | Cost | Unit | Cost | Unit | Cost | Unit | Duration | Cost | Unit | Cost | Unit | Cost | Enum | Enum | Boolean | ObjectId | Float | Enum | Date | String | ObjectId | ObjectId | ObjectId | ObjectId | ObjectId | ObjectId | ObjectId | ObjectId
1002 | CE1010 | CE1010 | 1018 | 1015 | Task Dependent | In Progress | 939 | 2014-02-03T00:00:00 | 2014-03-07T00:00:00 |  | 2014-04-09T00:00:00 |  |  |  | 2014-02-03T00:00:00 | 2014-03-07T00:00:00 | 2014-02-03T00:00:00 | 2014-03-07T00:00:00 | 2014-02-03T00:00:00 | 2014-03-07T00:00:00 |  | Duration |  | 10 | [19 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {D20DB099-C58B-475F-95A6-1136868B55D8}
1003 | CE1020 | CE1020 | 1018 | 1015 | Task Dependent | In Progress | 939 | 2014-02-08T00:00:00 | 2014-03-10T00:00:00 |  | 2014-04-15T00:00:00 |  |  |  | 2014-02-08T00:00:00 | 2014-03-10T00:00:00 | 2014-02-08T00:00:00 | 2014-03-10T00:00:00 | 2014-02-08T00:00:00 | 2014-03-10T00:00:00 |  | Duration |  | 35 | [19 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {66C92FC4-1C77-4F2A-8236-97A0F3FAA7DF}
1004 | CE1030 | CE1030 | 1018 | 1015 | Task Dependent | In Progress | 939 | 2014-03-10T00:00:00 | 2014-04-02T00:00:00 |  | 2014-04-30T00:00:00 |  |  |  | 2014-03-10T00:00:00 | 2014-04-02T00:00:00 | 2014-03-10T00:00:00 | 2014-04-02T00:00:00 | 2014-03-10T00:00:00 | 2014-04-02T00:00:00 |  | Duration |  | 20 | [19 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {32AE11C2-38A1-4AC3-A86C-7BF01AEFCB39}
1005 | CE1040 | CE1040 | 1018 | 1015 | Task Dependent | In Progress | 939 | 2014-04-08T00:00:00 | 2014-04-16T00:00:00 | [5 empty] | 2014-04-08T00:00:00 | 2014-04-16T00:00:00 | 2014-04-08T00:00:00 | 2014-04-16T00:00:00 | 2014-04-08T00:00:00 | 2014-04-16T00:00:00 |  | Duration | [21 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {8AC2AB94-703B-4393-92FA-A403DE7D3250}
1006 | CE1050 | CE1050 | 1018 | 1015 | Task Dependent | Not Started | 939 | 2014-05-17T00:00:00 | 2014-06-02T00:00:00 | [5 empty] | 2014-05-17T00:00:00 | 2014-06-02T00:00:00 | 2014-05-17T00:00:00 | 2014-06-02T00:00:00 | 2014-05-17T00:00:00 | 2014-06-02T00:00:00 |  | Duration | [21 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {D87DBE4F-D115-48C8-B885-E13B1D9183E2}
1008 | CE1070 | CE1070 | 1018 | 1016 | Task Dependent | In Progress | 939 | 2014-06-03T00:00:00 | 2014-07-08T00:00:00 |  | 2014-04-08T00:00:00 |  |  |  | 2014-06-03T00:00:00 | 2014-07-08T00:00:00 | 2014-06-03T00:00:00 | 2014-07-08T00:00:00 | 2014-06-03T00:00:00 | 2014-07-08T00:00:00 |  | Duration |  | 11 | [19 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {FF006130-6177-4946-A4F6-48869661C480}
1009 | CE1080 | CE1080 | 1018 | 1016 | Task Dependent | Not Started | 939 | 2014-07-08T00:00:00 | 2014-07-25T00:00:00 | [5 empty] | 2014-07-08T00:00:00 | 2014-07-25T00:00:00 | 2014-07-08T00:00:00 | 2014-07-25T00:00:00 | 2014-07-08T00:00:00 | 2014-07-25T00:00:00 |  | Duration | [21 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {88628A20-00EF-41BB-AB7F-13D64846C2A2}
1010 | CE1090 | CE1090 | 1018 | 1016 | Task Dependent | In Progress | 939 | 2014-07-28T00:00:00 | 2014-08-22T00:00:00 |  | 2014-04-23T00:00:00 |  |  |  | 2014-07-28T00:00:00 | 2014-08-22T00:00:00 | 2014-07-28T00:00:00 | 2014-08-22T00:00:00 | 2014-07-28T00:00:00 | 2014-08-22T00:00:00 |  | Duration |  | 35 | [19 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {8BC4F960-E81B-49A5-AE98-4E51083ACE68}
1012 | CE1110 | CE1110 | 1018 | 1017 | Task Dependent | In Progress | 939 | 2014-08-25T00:00:00 | 2014-09-19T00:00:00 | [5 empty] | 2014-08-25T00:00:00 | 2014-09-19T00:00:00 | 2014-08-25T00:00:00 | 2014-09-19T00:00:00 | 2014-08-25T00:00:00 | 2014-09-19T00:00:00 |  | Duration | [21 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {FDC8EF54-FA3F-45E6-9DE9-0915DF999A2A}
1013 | CE1120 | CE1120 | 1018 | 1017 | Task Dependent | In Progress | 939 | 2014-09-22T00:00:00 | 2014-10-08T00:00:00 |  | 2014-04-17T00:00:00 |  |  |  | 2014-09-22T00:00:00 | 2014-10-08T00:00:00 | 2014-09-22T00:00:00 | 2014-10-08T00:00:00 | 2014-09-22T00:00:00 | 2014-10-08T00:00:00 |  | Duration |  | 28 | [19 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {4AA63663-F3FC-4697-95B3-909F36503E59}
1014 | CE1130 | CE1130 | 1018 | 1017 | Task Dependent | Not Started | 939 | 2014-10-08T00:00:00 | 2014-10-17T00:00:00 | [5 empty] | 2014-10-08T00:00:00 | 2014-10-17T00:00:00 | 2014-10-08T00:00:00 | 2014-10-17T00:00:00 | 2014-10-08T00:00:00 | 2014-10-17T00:00:00 |  | Duration | [21 empty] | Fixed Duration and Units/Time | Normal | 1 |  | 1.00 |  |  | {9ABFD4DC-1C2F-4803-B28C-4039E9635CE9}

## Relationship
ObjectId | PredecessorActivityObjectId | PredecessorActivityId | PredecessorProjectObjectId | SuccessorActivityObjectId | SuccessorActivityId | SuccessorProjectObjectId | Type | Lag
ObjectId | ObjectId | String | ObjectId | ObjectId | String | ObjectId | Enum | Duration
1020 | 1002 | CE1010 | 1018 | 1003 | CE1020 | 1018 | Finish to Start | 1.000000
1021 | 1003 | CE1020 | 1018 | 1004 | CE1030 | 1018 | Finish to Start | 1.000000
1022 | 1004 | CE1030 | 1018 | 1005 | CE1040 | 1018 | Finish to Start | 1.000000
1023 | 1005 | CE1040 | 1018 | 1006 | CE1050 | 1018 | Finish to Start | 1.000000
1024 | 1008 | CE1070 | 1018 | 1009 | CE1080 | 1018 | Finish to Start | 1.000000
1025 | 1009 | CE1080 | 1018 | 1010 | CE1090 | 1018 | Finish to Start | 1.000000
1026 | 1012 | CE1110 | 1018 | 1013 | CE1120 | 1018 | Finish to Start | 1.000000
1027 | 1013 | CE1120 | 1018 | 1014 | CE1130 | 1018 | Finish to Start | 1.000000

## UDFType
ObjectId | DataType | SubjectArea | Title | IsSecureCode
ObjectId | Enum | Enum | String | Boolean

## ActivityCodeType
ObjectId | Name | Scope | Length | IsSecureCode | SequenceNumber | RefProjectObjectIds
ObjectId | String | Enum | Integer | Boolean | Integer | String

## ActivityCode
ObjectId | CodeTypeObjectId | CodeValue | Description | Color | SequenceNumber
ObjectId | ObjectId | String | String | String | Integer

## Expense
ObjectId | ActivityObjectId | ProjectObjectId | Description | CostAccountObjectId | PlannedCost | ActualCost | RemainingCost | AtCompletionCost | AutoComputeActuals | AccrualType | VendorId
ObjectId | ObjectId | ObjectId | String | ObjectId | Cost | Cost | Cost | Cost | Boolean | Enum | String

## Resource
ObjectId | Id | Name | Code | ResourceType | CalendarObjectId | CurrencyObjectId | DefaultUnitsPerTime | OvertimeFactor | IsActive | IsOverTimeAllowed | AutoComputeActuals | CalculateCostFromUnits | SequenceNumber | GUID | ParentObjectId | PrimaryRoleObjectId | ResourceNotes | UnitOfMeasureObjectId
ObjectId | String | String | String | Enum | ObjectId | ObjectId | Unit | Float | Boolean | Boolean | Boolean | Boolean | Integer | String | ObjectId | ObjectId | String | ObjectId